## Overview
Milestones
COMP285
Date | 2014-10-10 | 2014-10-11 | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18 | 2014-10-19 | 2014-10-20 | 2014-10-21 | 2014-10-22 | 2014-10-23 | 2014-10-24 | 2014-10-25 | 2014-10-26 | 2014-10-27 | 2014-10-28 | 2014-10-29 | 2014-10-30 | 2014-10-31 | 2014-11-01 | 2014-11-02 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07 | 2014-11-08 | 2014-11-09 | 2014-11-10 | 2014-11-11 | 2014-11-12 | 2014-11-13 | 2014-11-14 | 2014-11-15 | 2014-11-16 | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28 | 2014-11-29 | 2014-11-30 | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | 2014-12-08 | 2014-12-09 | 2014-12-10 | 2014-12-11 | 2014-12-12 | 2014-12-13 | 2014-12-14 | 2014-12-15 | 2014-12-16 | 2014-12-17
| Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday
Teacher Tasks | [6 empty] | HW2 |  |  |  | e-mail Deadline Requirements Paper | Presentation | [8 empty] | First Iteration | [14 empty] | Second Iteration | [20 empty] | Third Iteration |  |  |  | Final Pres |  | Final Pres | Final Pres |  |  |  | Final Pres
Milestones | [7 empty] | Draft of Requirement Paper
Angie | [6 empty] | PDF |  |  |  |  | PPP
Anthony | [6 empty] | PDF | Word |  |  | e-mail
Mike | [6 empty] | PDF | Word |  |  | e-mail

## Task Description
Task | due to | Content | Responsible person | in progrss/done
Requirements Paper | Monday 10/20 | Describe program requirements. | ?? (send email to Prof)
desribe functions and inputs
…
…
Program-Design Paper | ??? | Describe the design of the project implementation. The description should include English prose, UML diagrams and any viewgraphs necessary to elucidate the design. | ?? (put everything together in a nice IEEE-Format and send email to Prof)
Define structure
Define classes
Define methods
Define relationshiops between classes
|  | Draw UML Diagram | Angi
Iteration 1:
Subtasks for Iteration 1 |  | Read GameGrid Tutorials | Angi (selfstudy)
|  | Try to run and install GameGrid class | Angi (selfstudy)
|  | Try to create a game field | Angi (selfstudy)
|  | Study the math method for random apple method | Angi (selfstudy)
Anthony
Anthony
Mike
MIke
Iteration 1 | ??? | First round of implementing and testing. | ?? (send email to Prof)
|  | Create a GameGrid field for our Snake program | Angi
|  | Try to let an apple pop up on the field | Angi
Anthony
Anthony
MIke
MIke
Iteration 2:
Subtasks for Iteration 2 |  |  | Angi
Angi
Anthony
Anthony
Mike
MIke
Iteration 2 | ??? | Second round of implementing and testing. | ?? (send email to Prof)
Angi
Angi
Anthony
Anthony
MIke
MIke
Iteration 3:
Subtasks for Iteration 3 |  |  | Angi
Angi
Anthony
Anthony
Mike
MIke
Iteration 3 | ??? | Third round of implementing and testing. | ?? (send email to Prof)
Angi
Angi
Anthony
Anthony
MIke
MIke
Final presentation
Angi
Angi
Anthony
Anthony
Mike
MIke
Presenation | ??? | Presentation and Final Paper | ?? (send email to Prof)
Angi
Angi
Anthony
Anthony
MIke
MIke

## Milestone descriptions
Milestones | due | Content | Responsible person | in progrss/done
Reasearch | 2014-10-09 | Different links with example codes and tutorial sources of GameGrid | Angie (e-mail with word documents) | done
Study the example code | 2014-10-12 | Understand the code to be able to define our class definitions and milestones | all | Angie: done, Anthony: in progress, Mike: in progress
Draft of Requirements (IEEE Doc.) | 2014-10-17 | Describe the requirements of the prgram. The description should include English prose, UML diagrams and any viewgraphs necessary to elucidate the design. - Create the timetable with deadlines and resposibilites | all | in progress
Meeting with Prof | 2014-10-17 | Discuss our Design Paper before or after class | all | done
Revise and finish Requirements | 2014-10-19 | Add all suggestoins of the prof. and make changes and send it to Angie (that she can start with the presentation) | all | in progress
Deadline Requirements Paper | 2014-10-20 | e-mail with final Design Paper to Prof. | Mike (email to Prof)
Draft of Presentation | 2014-10-20 | Prepare presentation based on the revised Design Paper | Angie (PPP) | not started yet
Presentation of Requirements | 2014-10-21 | Hold the presentation in front of the class | Angie (PPP) | not started yet
| ??? | Meeting to discuss Design Paper | all
Design Paper | ?? | Describe the design of the project implementation. The description should include English prose, UML diagrams and any viewgraphs necessary to elucidate the design. - Create the timetable with deadlines and resposibilites - How many classes do we need - what kinf of reasearch must be made to be able to write the class - how does the classes relate to each other -> methods
| ?? | subtask of Iteration 1
| ?? | subtask of Iteration 1
| ?? | subtask of Iteration 1
Iteration 1 | 2014-10-30 | What must be done by now??
Iteration 2 | 2014-11-14 | What must be done by now??
Iteration 3 | 2014-12-05 | What must be done by now??
Finish whole project | ??? | Finish whole project* |  |  | * >> always finish 1-2 week ahead of deadline!
Meeting the Teacher for advice | ?? | Meeting the Teacher for advice
Finish and revise small details which were discussed | ?? | Finish and revise small details which were discussed
Finish Presentation | ?? | Finish Presentation
Practice presentation | ?? | Practice presentation | all
Final Presentation & Iteration 4 | 2014-12-09 | What must be done by now??