## Overview
Milestones
COMP285
Date | 2014-10-10 | 2014-10-11 | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18 | 2014-10-19 | 2014-10-20 | 2014-10-21 | 2014-10-22 | 2014-10-23 | 2014-10-24 | 2014-10-25 | 2014-10-26 | 2014-10-27 | 2014-10-28 | 2014-10-29 | 2014-10-30 | 2014-10-31 | 2014-11-01 | 2014-11-02 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07 | 2014-11-08 | 2014-11-09 | 2014-11-10 | 2014-11-11 | 2014-11-12 | 2014-11-13 | 2014-11-14 | 2014-11-15 | 2014-11-16 | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28 | 2014-11-29 | 2014-11-30 | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | 2014-12-08 | 2014-12-09 | 2014-12-10 | 2014-12-11 | 2014-12-12 | 2014-12-13 | 2014-12-14 | 2014-12-15 | 2014-12-16 | 2014-12-17
| Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday
Teacher Tasks | [6 empty] | HW2 |  |  |  | e-mail Deadline Deign Spec. Paper | Presentation | [8 empty] | First Iteration | [14 empty] | Second Iteration | [20 empty] | Third Iteration |  |  |  | Final Pres |  | Final Pres | Final Pres |  |  |  | Final Pres
Milestones | [7 empty] | Draft of Design Spec. Paper
Angie | [6 empty] | PDF |  |  |  |  | PPP
Anthony | [6 empty] | PDF | Word |  |  | e-mail
Mike | [6 empty] | PDF | Word |  |  | e-mail

## Task Description
Task | due to | Content | Responsible person | in progrss/done
Project Spec. Paper (Design) |  | Describe the design of the project implementation. The description should include English prose, UML diagrams and any viewgraphs necessary to elucidate the design.
Iteration 1 |  | First round of implementing and testing
Iteration 2 |  | Second round of implementaion and testing
Iteration 3 |  | Third round of implementation and testing
Final Presenation |  | Last round of impl. And testing & Summative Presentation

## Milestone descriptions
Milestones | due | Content | Responsible person | in progrss/done
Reasearch | 2014-10-09 | Different links with example codes and tutorial sources of GameGrid | Angie (e-mail with word documents) | done
Study the example code | 2014-10-12 | Understand the code to be able to define our class definitions and milestones | all | Angie: in progress, Anthony: in progress, Mike: in progress
Draft of Requirements (IEEE Doc.) | 2014-10-17 | Describe the design of the project implementation. The description should include English prose, UML diagrams and any viewgraphs necessary to elucidate the design. - Create the timetable with deadlines and resposibilites - How many classes do we need - what kinf of reasearch must be made to be able to write the class - how does the classes relate to each other -> methods | Anthony/Mike (word) | in progress
Meeting with Prof | 2014-10-17 | Discuss our Design Paper before or after class | all
Revise and finish Requirements | 2014-10-19 | Add all suggestoins of the prof. and make changes and send it to Angie (that she can start with the presentation) | Anthony/ Mike (word)
Deadline Requirements | 2014-10-20 | e-mail with final Design Paper to Prof. | Anthony (e-mail pdf)
Draft of Presentation | 2014-10-20 | Prepare presentation based on the revised Design Paper | Angie (PPP) | not started yet
Presentation of Requirements | 2014-10-21 | Hold the presentation in front of the class | Angie (PPP) | not started yet
Design Paper | ??
| ?? | subtask of Iteration 1
| ?? | subtask of Iteration 1
| ?? | subtask of Iteration 1
Iteration 1 | 2014-10-30 | What must be done by now??
Iteration 2 | 2014-11-14 | What must be done by now??
Iteration 3 | 2014-12-05 | What must be done by now??
Finish whole project | ??? | Finish whole project* |  |  | * >> always finish 1-2 week ahead of deadline!
Meeting the Teacher for advice | ?? | Meeting the Teacher for advice
Finish and revise small details which were discussed | ?? | Finish and revise small details which were discussed
Finish Presentation | ?? | Finish Presentation
Practice presentation | ?? | Practice presentation | all
Final Presentation & Iteration 4 | 2014-12-09 | What must be done by now??